## Matrix
2014-10-27 13:02 | iOS | Android | Web | Client API | Server API | UI/UX | Functional Progress | Estimate Date of Completion | Test Description | Comments | iPad Air iOS 7.0.6 | iPad 2 iOS 7.0.6 | iPhone 5 | iPhone 4s | iPhone 4 | Note 3 Android 4.4 | Note 3 Android 4.3 | Note 2 Android 4.3 | Note Android 4.1.2 | S5 Android | S4 Android | S3 Android
User/login | Done | Done | Done | Done | Done |  | 100% | Completed | User able to login through mobile number and passcode
User/logout | Done | Done | Done | Done | Done |  | 100% | Completed | User able to logout through logo>General>logout
User/profile | Done | Done | Done | Done | Done |  | 100% | Completed | User able to edit profile through logo>Settings>Edit User Profiles
User/Profile>Upload IC/Passport | Done | Done | Done |  |  |  | 60% |  | In Edit User Profile UI, user able to update the NRIC/Passport picture in the "Photo NRIC/Passport" tab
User/delete | Done | Done | Done | Done | Done |  | 100%
User/Suspend - Report Lost | Done | Done | Done | Done | Done |  | 100% | Completed
User/account info/check balance | Done | Done | Done | Done | Done |  | 100% |  | Balance will be show under setting logo>Settings>Wallet Balance
User/Add & Remove Cards (Debit Or Credit) | Done | Done |  | Done | Done |  | 80% |  | Has entry to add debit card, after click, it links to the MOLPay Card Payment site and unable to return
User/ Add & Remove Bank | Done | Done | Done | Done | Done |  | 100% |  | Settings Logo>Settings>Add Bank Accounts
User / Add & Remove Favourites | Done | Done | Done | Done | Done |  | 100% |  | Click on the love logo on the widget to fav or unfav
User/Register Trusted Device | Done | Done |  |  |  |  | 40% |  | Not found entry for this function
Credit
Add fund/MOLWallet PIN | Done | Done | Done | Done | Done |  | 100% |  | Add fund with physical outlet but the notification show RM0.00
Add fund/MOLPay | Done | Done | Done | Done | Done |  | 100%
Debit
Transfer > Request Money | Done | Done | Done | Done | Done |  | 100%
- Request Money > From Favourite MOLWallet ID | Done | Done |  |  |  |  | 40%
- Request Money > From User Nominate MOLWallet ID | Done | Done | Done |  |  |  | 60%
Transfer > Send Money | Done | Done | Done | Done | Done |  | 100%
-Send Money > Favourite MOLWallet | Done | Done |  |  |  |  | 40%
-Send Money> User nominate Number | Done | Done | Done |  |  |  | 60%
-Send Money>Invoices >Reject Request | Done | Done | Done |  |  |  | 60%
0%
Payment/Balance | Done | Done | Done | Done | Done |  | 100% |  |  | 1st use case is Telco Reload
Payment/MOLPay | Done | Done |  | Done | Done |  | 80% |  |  | 1st use case is faked merchant 2nd use Case will be real merchants
Cash out/ATM |  |  |  |  | Done |  | 20%
Cash out/Bank Account | Done | Done | Done | Done | Done |  | 100% | Completed
Features
Settings | Done | Done | WIP | Done | Done |  | 80%
Lock screen | Done | Done | Done | Done | Done |  | 100%
Notification | Done | Done | Done | Done | 0.8 |  | 80%
81.48%
Platform Progress | 96.3% | 96.3% | 74.07% | 70.37% | 70.37% | 0% | 67.9%
User/change ID | Phase 2 | Phase 2 | Phase 2 | Phase 2 | Phase 2 |  | 0% |  |  | Danny says skip this first
MOLWallet mobile SDK
User/login
User/logout
User/info
User/balance
Payment/request
Payment/pay
Payment/query
MOLWallet web API
Payment/request
Payment/pay
Payment/query
Admin Panel
Control for Merchants
Add Merchant Categories
Add Merchants & Logo
Add Merchant's Items & Picture
Order Merchant Categories
Select Merchant/Merchant Item for "Hot Picks"
Select Merchant Category/Merchant/Merchant Item for "Suggested"
User Profiles
View User Profile
Approvove / Suspend User Profile
Verify account via Uploaded IC/Passport & User entered informations
Note on A1: This violate PCI DSS compliance standard if we implement using Tap's API as it stores CVV, and it's not secure to store PAN on our own server. We'd better put this on hold first due to security reason. Use MOLPay 1-click first. -Tan Tek Jau
Note on G1: UI must be checked and approved by MOL team -Tan Tek Jau We may review UI on 22nd Jan 3pm -Tan Tek Jau
Note on G2: ios app need to add +601 hardcode android need to add + and minimize the gap -Tan Tek Jau
Note on A5: Delete App and clean up data on mobile device ---- View IC by 25/4 -Tan Tek Jau
Note on D5: Not applicable, only for mobile device
Note on E5: Not applicable
Note on F5: Not applicable, only for mobile device
Note on B6: Not applicable, only for web version
Note on C6: Not applicable, only for web version
Note on F6: will be removal after development phase -Ngo Minh Tap
Note on A12: 5 - 9/May -Tan Tek Jau
Note on E13: Not applicable
Note on F13: Not applicable
Note on E14: Not applicable
Note on F14: Not applicable
Note on A20: Allow all channels and cards first and later will remove credit card but allow debit card to top-up the wallet -Tan Tek Jau
Note on A22: Transfer Funds is considered completed for all platform, but "request Money" is a requirement missed out, so I reset the status. -Tan Tek Jau
Note on A31: 5 - 9/5 MOLPoints Google Wallet FB Credit -Tan Tek Jau
Note on A32: Please note that the front-end design (app/web/REST-CLIENT) must round the amount to 2-digit, as decimal and 1-digit number is not allowed. ATM cannot dispense coin or any amount less than RM10 -Tan Tek Jau Saadat, Waleed, Hairi pls ack on this when you see this message. Just reply here -Tan Tek Jau Ok. Mean that, for cash out ATM have a control on amount to cash out. -Hairizal Hanapi 5 - 9/May -Tan Tek Jau
Note on K32: This is a used case, shouldn't be listed here as it's part of payment/purchase function -Tan Tek Jau
Note on D36: WIP: 1. Add CC 2. View My QR Code 3. Add Favourite CC 4. Notification - Incomming invoice 5. Notification - Incomming transfer funds 6. About - MOLWallet 7. About - Help 8. About - Term & Condition Done: 1. Update information 2. Transaction History 3. View My Barcode 4. Create New Passcode 5. Reload Wallet (Just point to add funds) 6. Add Bank Acccount -Hairizal Hanapi
Note on A47: Must force logout before quiting SDK -Tan Tek Jau
Note on A51: Need to add card payment (all card type), can use new card. 28/4 - 2/5 -Tan Tek Jau
Note on A54: 28/4 - 2/5, API is ready for MOLPay, Av86 and WeShop integration -Tan Tek Jau
Note on F112: Not applicable
Note on F125: Not applicable

## ToDo
x | <--- put an "x" you have done or fixed the item in column A | Report by | Verify by | Remarks
All Platform
[ ] On lock screen, show the MOLWallet ID (mobile number): 601XXXX1689 <--- first 3 and last 4 only
[ ] Barcode should be a real one generated based on the MOLWallet ID instead of faked image (probably not applicable on web version)
[ ] "Suggested" function to promote selected merchants, can duplicate the "Favorite", required API from NL, I will inform Tap on this
[ ] "Favorite" function for Home(merchant), add fund, fund transfer, and cash out
[ ] Add "lock" screen icon, tentatively beside/to the left of the bell notification icon
[ ] Loading progress bar like web version when updating status/info
[ ] For iOS & Android, user clicks on email verification link to open the app, is this possible?
[ ] Number of retry allowed for Passcode (needs further discussion)
[ ] All links & Icon must be active (* able to click and link to website , App )
[ ] At least one channel in each Add Fund option must be active at launch ( Cash-7Eleven , Online Bank(1 bank), Debit Card )
[ ] Send OTP button , 1st OTP- 1minute (greyed out with coutndown timer) , 2nd OTP and subsequent OTP will be a 5 Minute interval.
[ ] Remove Notifications in Settings ( Feature to select Mobile / Email not implemented yet )
[ ] User should be able to add and delete most use functions to Favourites.
[ ] Include a counter for unread notification at "Bell" icon. Refer App GUI design . The counter "2" on bell icon.
[ ] Highlight all unread notifications.
[ ] All new notification should pop up briefly to notify user of incoming notification
APIs
[ ] web API - MOLPay team to discuss and tekjau to prepare doc
¦--- 1) Choose MOLPay to pay to merchant in MOLWallet
¦--- 2) Choose MOLWallet as a channel to pay in MOLPay payment page
[ ] mobile SDK - MOLPay team to discuss and tekjau to prepare doc
[ ] bill payment API - Sam will provide
x | [ ] MOLPoints PIN/PINless reload - Sam will provide
x | [ ] telco reload PIN
UI
[ ] MOLWallet logos in different dimensions
[ ] Languages spreadsheet - tekjau to prepare the doc
[ ] Standardize all front-end messages
Web
x | Remove all "Balance" bar from all pages.(update info, transfer fund , cash out, etc)
x | "Settings" scrollbar overlap with Internet Explorer Browser's scroll bar
x | Implement "Add Fund" beside balance with a "+" sign (*same as inside "settings") , clicking on "Balance" should display transaction history
x | Verify/Unverify MOLWallet status should be display along MOLWallet ID on the top bar. (*base on Paypal verified status)
Implement Smart App Banner (http://smartappbanners.com/) on the website. Whenever user browse molwallet.com on iOS devices, a banner appears on top of webpage telling user about the MOLWallet app in App Store.
Settings
- Account Information
x | Certain fields can't be activated and can't be updated
x | Dropdown menu for type of identification document ( IC or Passport ) .. if Passport , should have "Country of issue"
x | Should have field to upload Passport/IC photo
Partially Hashed Passport/IC number for privacy.
Use "Drop down" menu for birthday , DD / MM / YYYY (*Calendar too tedious)
x | Use "Drop up" menu for Country & State to maintain user browser view without need to scroll down main page
-Add Credit Card
x | Change "Add Credit Card" to "Add Debit Card"
x | Remove all reference of "Credit Card" , including "Add Favourite Credit Card"
Add Debit Card should ask for
1. Full Name *** not applicable
2. Debit Card Number (*implement debit card check digits format immediately)
3. Expiry Date
-Create new passcode
x | Reduce Passcode field size to match 6 digits
- Time-out (default 1 minute)
x | - User should be able to change default time out in User Settings ( 1 , 2 ,3 , 4, 5 minutes , Never )
Add Fund
Cash
Form validation is done in Pop-up screen(do not navigate away from page, error message display under text box)
x | 1. There is 16 digits PIN entered(any less will prompt error.. text box should only allow 16 digits max)
2. Display Used Pin status in Pop-up screen(* this if user have multiple PIN but not sure which one have been used previously. user can keep trying)
-Online Banking
MOLPay processing page should be launched in pop - up screen / new tab
-Transfer Fund
x | Google Chrome : Remove UP & DOWN arrow for "Amount"
Currency (MYR) should not be hardcoded
At the end of successful Transfer Fund , allow user to add MOLWallet ID (Mobile #) to Favourite Fund Transfer Payee.
Cash Out
x | OTP message - "OTP number will be send to your mobile"
x | Resend OTP - 1st Time - 1 Minute , 2nd and subsequent time will be 5 minutes interval
Note on B2: This will conflict with previous decision where the header always fixed on top, should do a scrolling instead -Tan Tek Jau
Note on B5: Tap, we need to duplicate "favorite" into "suggested" to highlight selected merchants for marketing purpose -Tan Tek Jau
Note on B6: Cannot mix all the favorite together. We have 4 main functions and each will has its own "Favorite" tab. -Tan Tek Jau
Note on B10: 3x attempt per device device will lock for 5 min -Tan Tek Jau Do we want to introduce captcha to avoid automation? -sam low
Note on B11: Add by Sam -sam low
Note on A14: Web version done.
Note on B28: Waiting for MOL IT Team to develop the Bill Payment backend before API can be provided. -sam low
Note on B29: Sam will try to get it by 24/1/2014 (Fri) -Tan Tek Jau API provided Jan 27 -sam low
Note on B41: Sam, we have 1) mobile verification 2) email verification 3) IC 4) IC photo which one are you referring to? -Tan Tek Jau I am referring to MOLWallet verified status for Cash Out. I am using Paypal's approach to let user know their account is not verified and there will be limitation to their MOLWallet -sam low
Note on B49: this one shouldn't be an issue as the wallet is already protected using Passcode -Tan Tek Jau Although it is protected by passcode , sensitive data like IC & Passport number shouldn't be shown... Please take Maybank credit card as example. They do not display full CC number in M2U. -sam low CC is CC, IC is IC -Tan Tek Jau CC is masked based on PCI compliance standard. If wanna follow Private Data Protection policies, then we can just show the first and last characters will do. -Tan Tek Jau If privacy is not a concern , then I am fine with it. -sam low Are we going to do this? -Hairizal Hanapi No concern with privacy. Will KIV for later -sam low
Note on B54: this suppose apply to all platform -Tan Tek Jau
Note on B55: Apply to all platform -Tan Tek Jau
Note on B80: There is no multi-currency support from the platform yet, always use 1 currency only -Tan Tek Jau OK -sam low
Note on B102: received from Sam on 27/1/2014

## Wishlist
Mobile App
[ ] User can rearrange all icon in App within its category - Added by Sam
Web
[ ] Transaction History - User should be able to select (check box) multiple receipt to be printed
Purchase Itunes Gift Card via MOL

## Web Issue List
Description | Priority | Status | Report by | Report Date | Reporter Remarks | Fix by | Remarks | Verify by | List Of Status
"Bill payment 1. Choose Biller 2. Enter Account number Remove Name ( for privacy issue) Amount = is an open value where User choose how much to pay .. not a fix value return from Server" 1. Choose Biller 2. Enter Account number Remove Name ( for privacy issue) Amount = is an open value where User choose how much to pay .. not a fix value return from Server |  |  | Sam | [5 empty] | Done
MOLPoints in Games & App = MOLPoints PIN/PINLESS purchase. |  |  | Sam | [5 empty] | In Progress
Forgot/Reset Passcode |  |  | Steph | [5 empty] | Pending
Can't generate Issue
No Issue

## IOS Issue List
Description | Priority | Report by | Report Date | Reporter Remarks | Status | Fix by | Remarks | Verify by | List Of Status
UI, especially the header must be consistent, use Android UI as benchmark |  |  |  |  | Done |  |  |  | Done
remove the grey background and expand the white content area to full height till it reaches the header and footer |  |  |  |  | Done |  |  |  | In Progress
add lock icon beside bell for quick screen lock function |  |  |  |  | Done |  |  |  | Pending
Change power icon in "Settings menu" beside Lock Screen to "lock icon" |  |  |  |  | Done |  |  |  | Can't generate Issue
Change Settings menu to follow iOS style (screen lock time) |  |  |  |  | Done |  |  |  | No Issue
Implement back button for all sub pages |  |  |  |  | Done
Barcode size to match Android version of MOLWallet |  |  |  |  | Done
Top Bar & MOLWallet logo Space, can be reduced to make more space for main menu |  |  |  |  | Done
Main Menus , 9 & 6 Icons design for different dimension |  |  |  |  | Done
[More...] to load next 9 icons page |  |  |  | Sam : not applicable anymore | No Issue
No Scrolling motion [fixed screen] if item display can fit in one screen. |  |  |  |  | Done
Update all UI to lastest. |  |  |  |  | In progress
Suggested Page must be 1st in page and focused on |  |  |  |  | Done | AJ
Favourite list must remain on APP even after logout |  |  |  |  | Done | AJ
Allow cut and paste of phone number from outside App. preset [601] interfere with copy paste of mobile number. Solution is open to suggestion |  |  |  |  | No Issue
Remove all screen loading message " Loading" , "updating account info" , "downloading question" .. etc |  |  |  |  | Done
Passcode not behaving consistently i.e. After not using the app for more than 12 hours, I opened the app and I saw no passcode screen. |  | LYH |  |  | Done | AJ |  | LYH
Delete copyright notice from the launch screen (?).. as it is not common among popular apps.
MOLWallet logo looks stretched (vertically) on both Log In and Register page?? |  |  |  |  | Done | AJ
Registration Form: Delete 'Step 1: |  |  |  |  | Done | AJ
Registration Form: use 'passcode' instead of 'M-Pin' |  |  |  |  | Done | AJ
After successfully complete the new user registration form (i.e correctly entered OTP and set passcode), user should be directed to the MOLWallet Home Screen rather than the Log In page. |  | LYH |  | [LYH] Do consider bypassing the Log In page after successful registration for better user experience. The lesser the friction, the better. | No Issue | AJ | The flow is same with android
Unlock: The screen should come with numeric keyboard showing, ready for user to input his passcode i.e. https://www.dropbox.com/s/als7zp39ccgdfmf/MOLWallet%20-%20Unlock.png |  | Sam | 2014-04-08 |  | Done | AJ | v.0.5.2.11
First Time Add Funds: No need for 'upload pic' icon for IC field. 'Upload pic' only appears during the Cash Out verification flow. |  | Sam | 2014-04-08 |  | Done
Button: Click 'Login' and 'Register' button, it has glow effect. Change press effect to change button background color when pressed (instead of the glow effect). |  | Sam | 2014-04-08
All Favourite pages in sub-menu would not be 1st focused. If empty , will look ugly. Eg. Transfer> should focus on "Send Money" instead of "Favourites" |  | Sam | 2014-04-08 |  | Done | AJ | v.0.5.2.11
iOS passcode lock screen , Add "Forgot Passcode" option for user to reset passcode |  | Sam |  |  | Done
Bill payment 1. Choose Biller 2. Enter Account number Remove Name ( for privacy issue) Amount = is an open value where User choose how much to pay .. not a fix value return from Server |  | Sam
Implement screen refresh to pull new data from server using " Swipe down to reload" |  | Sam
MOLPoints in Games & App = MOLPoints PIN/PINLESS purchase. |  | Sam
Forgot/Reset Passcode |  | Steph |  |  | Done
Spelling: Change 'Setting' to 'Settings' |  | Lim |  |  | Done
Account Information: No need the word 'Balance' besides the MYR, as the field label is called 'Wallet Balance' |  | Lim |  |  | Done
sending money to unverified account - Display "email" not verified (* should just display Number is not verified") |  |  |  |  | No Issue | AJ | From Server
Email verification notification - do not need be clickable Account transaction related - can be click . |  |  |  |  | Done
Request Money From other MOLWallet -When Click on notification , only show date and amount Need more details - Invoice / request number - Money Request from who, which MOLWallet ID? - Description |  |  |  |  | Done
After Successful Money Request, background "proceed" still clickable. Might caused duplicated request |  |  |  |  | Done

## Android Issue List
Description | Priority | Status | Report by | Report Date | Reporter Remarks | Fix by | Remarks | Verify by | List Of Status
Transfer fund software keyboard is masking on the description field | 1 | Done |  |  |  | Waleed |  |  | Done
[Back] button on phone will exit/crash the app when we are on the bank page, it suppose to back to the previous screen inside the app |  | Done |  |  |  | Waleed |  |  | In Progress
Circular sliding effect, means when we slide the screen from first page to the end, then start over again from first page, just like Android home screen, it's rotating. |  | Done |  |  |  | Waleed |  |  | Pending
Do not reset the displayed values while loading data |  | Done |  |  |  | Waleed |  |  | Can't generate Issue
Bill payment 1. Choose Biller 2. Enter Account number Remove Name ( for privacy issue) Amount = is an open value where User choose how much to pay .. not a fix value return from Server |  | Done | Sam | [5 empty] | No Issue
Implement screen refresh to pull new data from server using " Swipe down to reload" |  | not comptible with design | Sam
Bill Payment - after entering account # and proceed .. Cannot go back... |  | Done | Sam
[HOME] button not going home .. |  | Done | Sam
MOLPoints in Games & App = MOLPoints PIN/PINLESS purchase. |  | API NOT Ready | Sam
Forgot/Reset Passcode |  | Done | Steph
Trusted Device |  |  | MOL
Request OTP have no counter |  | Done
When install MOLWallet App, immediately make device default to add to trusted device. |  | Done
Trusted Device should be able to be "untrusted" |  | API Not Ready
Trusted Device management [ Available on Web only ] |  | API Not Ready
- > Before removal of trusted device, OTP(notification) send to targetted device to confirm |  | API Not Ready
Passcode retries . 3x then block for 1minute , thereafter 5 minute |  | Done | MOL
Settings > About |  |  | MOL
MOLWallet Version |  | Done
1st Time Intro ( Facebook sample , Overlay ) [ MOL Creative Team assist ]
Unverified status
Settings > edit Profile |  |  | MOL
Full Name > ok
Gender ; Default > "Please select gender" [ not "female" ]
Email , word cut off on the top on Samsung Note 2 |  | Done
View IC/Passport Photo - no photo uploaded = Ask User to upload [Currently only display black box] -Photo uploaded = Display uploaded photo |  | Done
Secret Question -> Father's Full Name still have error |  | Server issue
Duplicated Email used for different MOLWallet - > display proper error message |  | Server issue
Add Card Function - > need description to explain what it does and what is the benefits
"+" in the Setting page beside Wallet balance is too big |  | Done
Can MOLWallet ID at login screen be remembered so don't have to reenter every time?
Forgot Passcode on "Lock Screen" |  | Done
Email Verification -> option to resend to be added
Add banks doesn't show up in "Cash Out"->Bank |  | Done
Check Balance -> before allow purchase If Wallet =0 ; don't allow user to proceed to next screen
AV86, I choose to purchase item - Choose to pay with MOLWallet ; yet APP advice to download MOLWallet at login - Choose to pay with MOLWallet card; "What is MOLWallet Card?"
Add Fund -> after successful add fund , screen should refresh without previous PINS value |  | Done
Transaction History 1st Level - Simplified 2nd Level - Full details |  | please provide UI
Cash Out
ATM - MOLWallet ID -Generate OTP -Amount
Over The Counter - Transaction ID - OTP
Request Money - some fields hidden behind "Make another request" button - multiple can be done continuously |  | Done
Send Money -> invoice - Always Loading , transfer not successful. |  | Done
After account lock via [ I lost my phone ] - Try login -> "Invalid Data Parameters" - Should display message about MOLWallet being locked |  | Error should be changed in server
Remove "Reload Wallet" from Settings.. redundant |  | Done